## Release Backlog
Backlog ID | Backlog | STORY / FEATURE / REQUEST |  |  | Story ID | Priority | Business Value | Sprint# | State | Note
|  | As a/an [User role] | I want to [Goal] | So that [reason]
PB01 | Quan ly tin nhan | User | Set the start time, end time, and content will be sent SMS messages | I can remind customers to car maintenance in each time | RQ04 | 1 | High | 1 | New
|  | User | Have the program which automatically send a message each day | I can announce to customer who have enough conditions in the RQ04 and is not sended messages about my vehicle maintenance program | RQ05 | 1 | High | 1 | New
|  | User | Send the message to all my customer | We can send a message again when it has been error | RQ06 | 1 | High | 1 | New
|  | User | Review the history of messages sent to customers. | I know my program which implement well and all my customer know it | RQ10 | 3 | Medium | 1 | New
PB02 | Quan ly thong tin khach hang | User | Print a list of customers coming to the birthday | We can send a birthday card or a birthday message | RQ07 | 3 | High | 1 | New
| Quan ly thong tin khach hang | User | View my customer's information which like SMS Template.xls | I can manage the information of customer who buy my motorbikes | RQ02 | 2 | Medium | 1 | New
| Quan ly thong tin khach hang | User | Import my customer's information from file excel (like SMS Template.xls) | I can create the list of customer's information quickly | RQ03 | 2 | High | 1 | New
PB03 | Quan ly xe | User | View my motorbike's information include : categories, colors, price, inventory | I can manage the information of motorbike in my superstore | RQ08 | 3 | High | 1 | New

## Product Backlog
ID | STORY / FEATURE / REQUEST |  |  | Priority | Business Value | Acceptance Criteria | State | Note
| As a/an [User role] | I want to [Goal] | So that [reason]
RA1 | User | Giao diện đăng kí, đăng nhập | Khách hàng và nhân viên có thể tạo tài khoản ngân hàng và đăng nhập vào tài khoản của chính mình | 1 | Medium
RA2 | User | Giao diện dành cho admin | Quản lý toàn bộ thông tin khách hàng và thông tin nhân viên | 5 | Medium
RA3 | User | Giao diện dành cho nhân viên ví điện tử Rabit | Giúp nhân viên quản lý và thực hiện thao tác giao dịch | 1 | Medium
RA4 | User | Giao diện dành cho khách hàng | Cho phép khách hàng có thể quản lý tài khoản và thao tác giao dịch của mình qua hệ thông | 1 | Medium
RA5 | User | Rút tiền, chuyển tiền, nạp tiền | Phục vụ theo nhu cầu và yêu cầu của khách hàng. | 2 | High
RA6 | User | Cập nhật thông tin cho khách hàng và nhân viên | Nhằm giúp khách hàng và nhân viên có thể chỉnh sửa lại thông tin cá nhân | 2 | Medium
RA7 | User | Nhân viên tìm thông tin khách hàng, admin tìm thông tin nhân viên | Hỗ trợ nhân viên tìm thông tin khách hàng một cách nhanh chóng. | 2 | Medium
RA8 | User | Xem lại lịch sử giao dịch | Khách hàng có thể kiểm tra lại lịch sử giao dịch và nhân viên có thể quản lý lịch sử giao dịch của toàn khách hàng | 3 | Medium
RA9 | User | Có thể xoá thôngt tin nhân viên và thông tin khách hàng | Admin có quyền xoá thông tin nhân viên và xoá thông tin khách hàng, Nhân viên có thể xoá thông tin và tài khoản của khách hàng theo yêu cầu của khách hàng hoặc do khách hàng không đủ điều kiện giữ tài khoản | 4 | Medium
RA10 | User | Tính bảo mật của tài khoản khách hàng | Nhằm bảo vệ quyền lợi, bảo mật tài khoản khách hàng tránh bị đánh cắp thông cá nhân. | 5 | High

## RULE
Title: Brief description of the PBI. The title of a PBI should represent the intent of the PBI.
Iteration: Indicate the sprint in which a PBI is implemented. When you first enter a PBI into TFS, iteration defaults to the current project, meaning that it's not yet scheduled for a sprint. During the sprint planning meeting, when the team commits to implementing a PBI, you set this field to the iteration representing the sprint.
Assigned To: Indicates the owner of a PBI. The product owner who's assigned to the PBI is responsible for answering questions and providing details about the PBI. This person is also responsible for verifying that the PBI meets acceptance criteria before the team finishes the sprint. When a PBI is first created, the Assigned To field defaults to the user entering the PBI, so it's best to set it to the product owner at that point.
State: Use the State field to track the current state of a PBI.
New: The PBI is entered into TFS. It may be just the initial text of a user story, or it may be fully defined with test cases and acceptance criteria.
Approved: The PBI has been approved by the product owner and is a candidate to be assigned to a sprint at the sprint planning meeting.
Committed: The PBI has been assigned to a sprint, and the team has committed to completing it.
Removed: The PBI is no longer needed. This is useful when you're pruning the backlog to remove duplicates, to consolidate similar PBIs, or to simply remove the PBIs that are such low priority that they will never be built.
Done: The PBI is complete, and the product owner has tested and verified it.
Reason: Reason is a read - only field that is predefined based on the state and transition of the PBI.
New
New Backlog Item : The PBI was just entered but not yet prioritized or estimated.
Reconsidering Backlog Item : The item had been removed but was reconsidered and is now back in the backlog.
Approved
Approved by the Product Owner : The PBI was approved by the product owner and is now ready to be included in a sprint.
Work Stopped : The PBI had been committed to a sprint, but the team decided to stop work on it and put it back in the backlog for future sprint.
Committed : Commitment Made by the Team : The team has committed to implement the PBI in a sprint.
Additional Work Found: The PBI was previously considered done, but more work was found, so it's back in the backlog.
Removed: The PBI was removed from the backlog.
Done: The work on the PBI is finished.
Backlog Priority: Used to determine the position of the PBI on the product backlog. New PBIs default to a backlog priority of 1,000. This field represents an item's location in the backlog, not its business value. It indicates when the PBI should be scheduled, relative to other items on the list.
Effort: Used to track the estimated effort required to implement a PBI, relative to other PBIs in the release. Relative is the operative word here, as the effort is not in terms of hours or days. Rather, it's a just a number used to compare the relative effort required for PBIs.
Business Value: Used to track the amount of business value delivered by a PBI. You should choose a number between 1 and 100 to represent the amount of business value that implementing the PBI will deliver to your customers. Higher numbers imply greater business value. A PBI with a low business value and a high effort estimate probably won't get scheduled into a sprint and will remain on the product backlog.
Description: Used to provide a detailed description of a PBI. This is where the product owner describes what the feature does and who needs it. If you're defining PBIs via user stories, then this is the written record of the feature.
Acceptance Criteria: Used to provide a bulleted list of criteria a PBI must meet before it will be accepted as done. The product owner defines the acceptance criteria either when initially creating the PBI or when the PBI is added to a sprint. It's critical to have sufficient information in this field for a PBI because these are the criteria against which the team will build the feature during the sprint.
Conclusion
In this article, we have seen that the product backlog is the list of requirements for the system. It is the central focus of a Scrum team, representing the features that the team will build into the product. The product owner defines and prioritizes the PBIs. Each PBI stores the details of one product feature. It describes its business benefit, test cases, and acceptance criteria.

## Sprint Backlog
Sprint Back Log
Task ID | Task | Description | Story ID | Backlog ID | Sprint# | State | Estimate Time (Hours) | Assign to | Note
Form đăng nhập, đăng kí
T01 | Đăng nhập | Check thông tin người dùng để xem là chức vụ phù hợp của người sử dụng |  | PB01 |  | New | 2 | Huy Hoàng
T02 | Đăng kí | Đưa tất cả thông tin mà mình đăng kí vào database, sau đó dùng thông tin đó để login |  |  |  | New | 2 | Huy Hoàng
T03 | Quên mật khẩu | Gửi mã xác nhận qua mail hoặc sđt của khách hàng | RQ04 |  | 1 | New | 2 | Huy Hoàng
T04 | Đổi mật khẩu | Đổi mật khẩu theo nhu cầu của khách hàng |  |  | 1 | New | 2 | Huy Hoàng
T05 | Liên hệ tư vấn | Liên hệ với nhân viên tư vấn để được hỗ trợ tra cứu thông tin tài khoản, tìm kiếm các vấn đề, quản lý tài chính cá nhân và các thông tin hữu ích khác | RQ05 |  | 1 | New | 2 | Huy Hoàng
T06 | Hỏi đáp | Danh sách câu hỏi và câu trả lời về giải đáp thắc mắc | RQ10 |  | 1 | New | 2 | Huy Hoàng
Form do người dùng sử dụng
T7 | Thông báo | Thông báo và quảng cáo về những dịch vụ đang và sắp có trong tương lai |  | PB02 |  |  | 3 | Ngọc An
T8 | Nạp tiền từ thẻ qua ví | Nạp tiền do khách hàng nạp | RQ02 RQ03 |  | 1 | New | 3 | Ngọc An
T9 | Chuyển tiền | Chuyển tiền cho người dùng khác |  |  | 1 | New | 3 | Thanh Hà
T10 | Thanh toán | Thanh toán hóa đơn, các dịch vụ cho vay |  |  | 1 | New | 2 | Thanh Hà
T11 | Nạp tiền điện thoại | Khách hàng có thể nạp tiền điện thoại với tiền trong ví
T12 | Quét mã QR | Tạo ra mã QR để thanh toán
T13 | Tìm bạn bè bằng SĐT | KB để cho giao dịch được thuận tiện
T14 | Tích điểm | Tích điểm đổi những phần quà có giá trị
T15 | Quản lí chi tiêu theo tháng
T16 | Goal Save(Thiết lập mục tiêu)
T17 | Hũ tiết kiệm
T18 | Liên kết tài khoản ngân hàng vào ví | Để liên kết ngân hàng với ví điện tử
Form do nhân viên Rabbit Ví
T19 | Tìm kiếm thông tin | Tìm kiếm thông tin, lịch sử giao dịch của khách hàng |  | PB03 |  |  | 3 | Bình An
T20 | Thêm | Thêm khách hàng mới
T21 | Xóa | Xóa thông tin khách hàng
T22 | Cập Nhật | Cập nhật thông tin khách hàng
T23 | Hiển thị thông tin khách hàng | Khách hàng có thể xem thông tin lịch sử giao dịch, số dư của mình
T24 | Nạp tiền | Nạp tiền vào ví do nhân viên nạp
T25 | Xử lý trạng thái giao dịch | xử lý trạng thái giao dịch thành công hay chưa |  |  | 1 | New | 6 | Phạm Ngọc
Form của admin
T26 | Bảng xem thông tin khách hàng | [5 empty] | 2 | Huy
T27 | Thêm nhân viên | Thêm nhân viên mới |  |  |  |  | 3 | Huy
T28 | Cập nhật nhân viên | Cập nhật lại thông tin nhân viên | RQ08 | PB03 | 1 | New | 4 | Huy
T29 | Tìm nhân viên | Tìm nhân viên theo mã nhân viên |  |  | 1 | New | 1 | Huy
T30 | Xem toàn bộ danh sách nhân viên | Giúp admin quản lý toàn bộ nhân viên |  | PB03 |  |  | 3 | Bình An
T31 | Xóa nhân viên | Xóa nhân viên khi nhân viên nghỉ việc |  |  | 1 | New | 1
T32 | Khóa tài khoản | Khóa tài khoản của khách nếu nhập sai pass hoặc khóa theo yêu cầu khách hàng

## Tính điểm Sprint
| Đặc Điểm |  |  |  | Tổng UP (Điểm chưa hiệu chỉnh) | Hệ số Nhân | AP (Điểm đã hiệu chỉnh) | ED (Khía cạnh môi trường) | PPS ((AP * ED)/36)
| Loại tương tác | Quy tắc nghiệp vụ | Thực thể | Loại thao tác Dữ liệu
Sprint 1
Đăng nhập | 3 | 2 | 2 | 1 | 8 | 1 | 8 | 16 | 3.5556 | Đợt 1 | 35.1111
Đăng kí | 3 | 2 | 2 | 2 | 9 | 1 | 9 | 16 | 4
Quên mật khẩu | 3 | 2 | 2 | 2 | 9 | 1 | 9 | 16 | 4
Đổi mật khẩu | 3 | 2 | 2 | 2 | 9 | 1 | 9 | 16 | 4
Liên hệ tư vấn | 3 | 1 | 1 | 1 | 6 | 1 | 6 | 16 | 2.6667
Hỏi đáp | 3 | 1 | 1 | 1 | 6 | 1 | 6 | 16 | 2.6667
Thêm khách hàng | 3 | 2 | 2 | 2 | 9 | 1 | 9 | 16 | 4
Xóa thông tin KH | 2 | 1 | 2 | 1 | 6 | 1 | 6 | 16 | 2.6667
Cập nhật thông tin KH | 3 | 2 | 2 | 3 | 10 | 1 | 10 | 16 | 4.4444
Liên kết tài khoản ngân hàng vào ví | 3 | 1 | 1 | 2 | 7 | 1 | 7 | 16 | 3.1111
Sprint 2 | [9 empty] | Đợt 2 | 27.1111
Nạp tiền | 3 | 2 | 2 | 3 | 10 | 1 | 10 | 16 | 4.4444
Nạp tiền nạp tiền từ thẻ ngân hàng qua ví | 3 | 2 | 2 | 3 | 10 | 1 | 10 | 16 | 4.4444
Nạp tiền điện thoại | 3 | 2 | 2 | 3 | 10 | 1 | 10 | 16 | 4.4444
Chuyển tiền | 2 | 2 | 2 | 3 | 9 | 1 | 9 | 16 | 4
Thanh toán | 2 | 2 | 2 | 3 | 9 | 1 | 9 | 16 | 4
Cập nhật thông tin KH | 3 | 1 | 1 | 3 | 8 | 1 | 8 | 16 | 3.5556
Hiển thị thông tin người dùng, lịch sử giao dịch, số dư | 1 | 1 | 2 | 1 | 5 | 1 | 5 | 16 | 2.2222
Thông báo(quảng cáo, giao dịch,….) | 1 | 1 | 1 | 1 | 4 | 1 | 4 | 16 | 1.7778
Quét mã QR thanh toán (LK nhiều bên)
Sprint 3
Tìm kiếm thông tin và lịch sử giao dịch khách hàng | 3 | 1 | 1 | 1 | 6 | 1 | 6 | 16 | 2.6667
Xử lý trạng thái giao dịch | 2 | 1 | 2 | 3 | 8 | 1 | 8 | 16 | 3.5556
Quản lí chi tiêu theo tháng | 3 | 2 | 2 | 3 | 10 | 1 | 10 | 16 | 4.4444
Goal save (Thiết lập mục tiêu) | 2 | 2 | 2 | 3 | 9 | 1 | 9 | 16 | 4
Hũ tiết kiệm | 3 | 3 | 3 | 3 | 12 | 1 | 12 | 16 | 5.3333
Sprint 4 | [9 empty] | Đợt 4 | 20
Bảng xem thông tin khách hàng | 1 | 1 | 1 | 1 | 4 | 1 | 4 | 16 | 1.7778
Thêm nhân viên | 3 | 2 | 1 | 3 | 9 | 1 | 9 | 16 | 4
Khóa tài khoản | 3 | 1 | 1 | 3 | 8 | 1 | 8 | 16 | 3.5556
Tìm bạn bè bằng số điện thoại | 3 | 3 | 2 | 1 | 9 | 1 | 9 | 16 | 4
Tích điểm khách hàng | 2 | 3 | 2 | 3 | 10 | 1 | 9 | 16 | 4
Tìm nhân viên | 3 | 1 | 1 | 1 | 6 | 1 | 6 | 16 | 2.6667
Tổng (+Sprint) | [7 empty] | 464 | 104

## Điểm của các khía cạnh mt(ED)
Khía cạnh tổ chức
Yếu Tố | Khoảng điểm
1. Đã có những phòng ban khác nhau cùng làm việc thành công trong một dự án Scrum? | 0
2. Có sự chống đối mạnh mẽ với Scrum trong tổ chức? | 2
3. Có tồn tại sự hỗ trợ lớn về Scrum giữa những phòng ban khác nhau trong công ty? | 1
Khía cạnh hạ tầng phát triển
Yếu Tố | Khoảng điểm
1. Kiểm thử tự động được áp dụng và trở thành một kĩ thuật phổ biến hay chưa? | 0
2. Kiểm thử tích hợp liên tục đã được áp dụng và trở thành một kĩ thuật phổ biến hay chưa? | 0
3. Môi trường xây dựng hằng ngày đã được áp dụng và trở thành một kĩ thuật phổ biến hay chưa? | 0
Khía cạnh nhóm
Yếu Tố | Khoảng điểm
1. Scrum là hoàn mới đối với nhóm | 2
2. Các thành viên trong nhóm đã từng làm việc thành công với nhau | 0
3. Các thành viên trong nhóm hiểu và tôn trọng lẫn nhau | 2
Khía cạnh công nghệ
Yếu Tố | Khoảng điểm
1. Nhóm phát triển có nhiều kinh nghiệm với ngôn ngữ lập trình | 1
2. Các thành viên trong nhóm có nhiều kinh nghiệm với công nghệ được sử dụng | 1
3. Môi trường sản xuất với scrum đã sẵn sàng chưa | 2
Khía cạnh quy trình
Yếu Tố | Khoảng điểm
1. Scrum có phải là khung làm việc được chấp thuận trong cty hay ko ? | 2
2. Trong cty có sự hỗ trợ tốt cho Scrum hay ko? | 2
3. Trong Cty có sự phản đối với Scrum hay ko ? | 0
Khía cạnh nhiệp vụ
Yếu Tố | Khoảng điểm
1. Có 1 product owner nào hoàn toàn sẵn sàng và gắn bó lâu dài với nhóm hay ko? | 1
2. Có phải product owner đã quen thuộc vs scrum nhưng vẫn thiếu kinh nghiệm thực tế | 0
3. Product owner đã từng thành công với Scrum trước đây hay chưa? | 0