## Revision history
Document Reviewer Information
Reviewer Name | Review Attendance (R/S) | Comments
R/S: Required or Suggested participants or functions for the document review meeting
Document Approver Information
Approver Name | Approver Function | Comments
Document Revision History
Date | Revision | Status | Change Summary | Revised by
07/26/2011 | 0.1 | Plan |  | Anh Lam
2011-05-08 | 0.2 | Close | Update System Test | Anh Lam
2011-08-08 | 1.0 | Close | Update Unit Test | Phuong Le

## System test report
Defect report (System test)
Defect ID | Defect title | Assigned to | State | Priority (1,2,3,4) | Severity (1,2,3,4) | Occurences | Created by | Date created | Re-produce steps | Detail | System info | Related Testcase ID
Statistical
QLNCC_DF_RP01 | Đăng kí | Tâm | fail | 3 | 2 | chưa hiển thị được bản thận đăng nhập ở vai trò nào của admin hay user | Lành | 2021-08-11 | Thêm phần chức vụ user hoặc admin. | Thêm chức vụ sau đó liên kết với cơ sở dữ liệu. |  | QLCH_NCC06
QLNCC_DF_RP02 | Sửa sản phẩm | Thịnh | fail | 3 | 2 | khi chọn hiển thị sản phẩm thì thông tin sản phẩm được lưu nhưng hình ảnh của sản phẩm chưa có. | Lành | 2021-08-12 | Thêm hình ảnh | Thêm hình ảnh sản phẩm |  | QLCH_TK02
Product category Manage
QLCH_DF_DMMH01 | add new product category | Thanh Tran, Tram Tran | Close | 1 | 1 | program will add the product category | Anh Lam | 07/27/2011 | 1. Select category to add new child category 2. Click right mouse and select "Tạo mới danh mục" 3. Program will show new pproduct category with name is “Danh mục mới” and Actor can change name of it. 4. Actor change name of new pproduct category and Enter. 5. Program show message: "Danh mục đã tồn tại". | the new product category and last product category, they have same name. |  | ST-F-DM01
QLCN_DF_DMMH02 | change name of product category | Thanh Tran, Tram Tran | Close | 1 | 1 | Same name | Anh Lam | 07/27/2011 | 1. Select the pproduct category, click right mouse 2. Seclect: "Đổi tên danh mục" 4. Actor change name it and Enter. 4. Programe show message: "Trùng tên danh mục" | Product has in interface |  | ST-F-MH04
Promote Manager
QLCN_DF_MK01 | create new promote | Tuan Ly | Close | 1 | 1 | don't fix defect | Anh Lam | 07/27/2011 | 1. select "add" :create promote 2. input name of promote , select create date and effective date. 3. click "Lưu vào danh bạ" 4. Program will be save in database | they have same name.
Pproduct manage
QLCN_DF_HDDH01 | progaram show message | Phuong Le | Close | 1 | 1 | miss information of product | Anh Lam | 07/27/2011 | 1. Select: " nhập liệu thông tin" 2. Program show all Textbox which input information 3. Input all information Click "Lưu vào danh sách" 4. Program show message: “Mặt hàng đã tồn tại trong danh mục” . | miss information of product |  | ST-F-DH02

## Unit test report
Defect report (Unit test)
Defect ID | Defect title | Assigned to | State | Priority (1,2,3,4) | Severity (1,2,3,4) | Occurences | Created by | Date created | Re-produce steps | Detail | System info | Related Testcase ID
ConnectData.cs
UT-DF-CD01 | GetTopDataCell(string nameTable, string nameSelectColumn, string orderByColumn) | Tuan Ly | Close | 1 | 2 | This Function return wrong value | Phuong Le | 2011-04-08 | Execute GetTopDataCell(string nameTable, string nameSelectColumn, string orderByColumn) with parameters are: NHOMHANG, MANHAN, MANHAN | In table NHOMHANG don't have column MANHAN, but this function return value 55 |  | UT-CD03
KhuyenMaiCtrl.cs
UT-DF-KMC01 | KiemTraTruocKhiLuu(DataTable dtbKhuyenMai, String cellString) | Hung Tran | Close | 1 | 1 | This function can't test TENKM when it is null | Phuong Le | 2011-04-08 | Execute KiemTraTruocKhiLuu(DataTable dtbKhuyenMai, String cellString) with parameters are: (2,"",1, 19/8/2011, 4/8/2011), "TenKM" | It miss check TenKM be null |  | UT-KMC01
UT-DF-KMC02 | KiemTraTruocKhiLuu(DataTable dtbKhuyenMai, String cellString) | Hung Tran | Close | 1 | 1 | This function can't test TENKM when it is more 50 characters | Phuong Le | 2011-04-08 | Execute KiemTraTruocKhiLuu(DataTable dtbKhuyenMai, String cellString) with parameters are: (2,“Chương trình khuyến mãi mừng ngày Thầy thuốc Việt Nam 27-2”1, 19/8/2011, 4/8/2011), "TenKM" | It miss check TenKM be more 50 characters |  | UT-KMC01
MatHangKhuyenMaiCtrl.cs
UT-DF-MHKMC01 | KiemTraTruocKhiLuu(DataTable dtbMatHangKhuyenMai, String cellString) | Hung Tran | Close | 1 | 1 | This function can't check the product is be sale off in other program | Phuong Le | 2011-04-08 | Execute KiemTraTruocKhiLuu(DataTable dtbKhuyenMai, String cellString) with parameters are: (2 ,54,1 ,5/08/2011 12:00:00 SA ,10/08/2011 12:00:00 SA, 4000), "MaMH" (2,53 ,1, 5/08/2011 12:00:00 SA ,10/08/2011 12:00:00 SA, 4000),"MaMH" | The Product with code 53,54 is promoting in first program, but in second it add a new program with beginning when the first program hasn't finished. |  | UT-MHKMC01
NhaCungCapCtrl.cs
UT-DF-NCCC01 | KiemTraTruocKhiLuu(DataTable dtbNhaCungCap, String cellString) | Anh Lam | Close | 1 | 2 | This function can't test TenNhaCungCap when it is more 100 characters | Phuong Le | 2011-04-08 | Execute KiemTraTruocKhiLuu(DataTable dtbNhaCungcap, String cellString) with parameters are: 1,CÔNG TY TRÁCH NHIỆM MỘT THÀNH VIÊN THỰC PHẨM DINH DƯỠNG VÀ NƯỚC GIẢI KHÁT MIỀN NAM – PEPPCOO1,“0831854245”,“1795178572”,TPHCM,“081672172”,1,TenNhaCungCap | It miss check TenNhaCungCap be more 100 characters |  | UT-NCCC01
UT-DF-NCCC02 | KiemTraTruocKhiLuu(DataTable dtbNhaCungCap, String cellString) | Anh Lam | Close | 1 | 2 | This function can't test SoDT when it is more 20 characters and include numbers | Phuong Le | 2011-04-08 | Execute KiemTraTruocKhiLuu(DataTable dtbNhaCungcap, String cellString) with parameters are: 1,GRAFIGHT,083185424508318542451,1795178572,TPHCM,081672172,1,SoDT | It miss check SoDT be more 20 characters |  | UT-NCCC01
UT-DF-NCCC03 | KiemTraTruocKhiLuu(DataTable dtbNhaCungCap, String cellString) | Anh Lam | Close | 1 | 2 | This function can't test SoTaiKhoan when it is more 20 characters | Phuong Le | 2011-04-08 | Execute KiemTraTruocKhiLuu(DataTable dtbNhaCungcap, String cellString) with parameters are: 1,GRAFIGHT,“0831854245”,“1795178572D1795178572”,TPHCM,“081672172”,1,SoTaiKhoan | It miss check SoTaiKhoan be more 20 characters |  | UT-NCCC01
UT-DF-NCCC04 | KiemTraTruocKhiLuu(DataTable dtbNhaCungCap, String cellString) | Anh Lam | Close | 1 | 2 | This function can't test SoTaiKhoan with special characters | Phuong Le | 2011-04-08 | Execute KiemTraTruocKhiLuu(DataTable dtbNhaCungcap, String cellString) with parameters are: 1,GRAFIGHT,“0831854245”,“1795178572D1795178$”,TPHCM,“081672172”,1,SoTaiKhoan | SoTaiKhoan can't have special characters |  | UT-NCCC01
UT-DF-NCCC05 | KiemTraTruocKhiLuu(DataTable dtbNhaCungCap, String cellString) | Anh Lam | Close | 1 | 2 | This function can't test DChi when it is more 100 characters | Phuong Le | 2011-04-08 | Execute KiemTraTruocKhiLuu(DataTable dtbNhaCungcap, String cellString) with parameters are: 1,GRAFIGHT,“0831854245”,“1795178572”,57-59-61-63/159/12/9923 NGUY?N TH? MINH KHAI - PHƯ?NG TR?N HƯNG Đ?O - THÀNH PH? V?NG TÀU - BÀ R?A V?NG TÀU,“081672172”,1,Dchi | Dchi cannot null anh less 100 characters
UT-DF-NCCC06 | KiemTraTruocKhiLuu(DataTable dtbNhaCungCap, String cellString) | Anh Lam | Close | 1 | 2 | This function can't test SoFax when it is more 20 characters and include numbers | Phuong Le | 2011-04-08 | Execute KiemTraTruocKhiLuu(DataTable dtbNhaCungcap, String cellString) with parameters are: 1,GRAFIGHT,“0831854245”,“1795178572”,TPHCM,“083185424508318542451”,1,SoFax,false | It miss check SoFax be more 20 characters
MatHangCtrl.cs
UT-DF-MHC01 | KiemTraTruocKhiLuu(DataTable dtbMatHang, String cellString) | Thanh Tran, Tram Tran | Close | 1 | 1 | It can't check same barcode | Phuong Le | 2011-04-08 | Execute KiemTraTruocKhiLuu(DataTable dtbMatHang, String cellString) with parameters are: 2,“8012441555100”, GILLETTE FUSION PROGLIDE , 100 , P&G , False , NULL , CÁI ,8000, 17,MaVach | It is same product barcode in store |  | UT-MHC01
UT-DF-MHC02 | KiemTraTruocKhiLuu(DataTable dtbMatHang, String cellString) | Thanh Tran, Tram Tran | Close | 1 | 1 | TenMH is more 50 characters | Phuong Le | 2011-04-08 | Execute KiemTraTruocKhiLuu(DataTable dtbMatHang, String cellString) with parameters are: 2,“8012441555101”, D?u g?i đ?u ADVANCE TECHNIQUES Body Building Shampoo , 100 , P&G , False , NULL , CÁI ,8000, 17, TENMH | It miss check TenMH be more 50 characters |  | UT-MHC01
UT-DF-MHC03 | KiemTraTruocKhiLuu(DataTable dtbMatHang, String cellString) | Thanh Tran, Tram Tran | Close | 1 | 1 | NSX is more 100 characters | Phuong Le | 2011-04-08 | Execute KiemTraTruocKhiLuu(DataTable dtbMatHang, String cellString) with parameters are: 2,“8012441555101”, SODA , 100 , CÔNG TY TRÁCH NHI?M M?T THÀNH VIÊN TH?C PH?M DINH DƯ?NG VÀ NƯ?C GI?I KHÁT MI?N NAM – PEPPCOO1 , False , NULL , CÁI ,8000, 17, NSX,false | It miss check NSX be more 100 characters |  | UT-MHC01
UT-DF-MHC04 | KiemTraTruocKhiLuu(DataTable dtbMatHang, String cellString) | Thanh Tran, Tram Tran | Close | 1 | 1 | DVTinh is more 10 character | Phuong Le | 2011-04-08 | Execute KiemTraTruocKhiLuu(DataTable dtbMatHang, String cellString) with parameters are: 2,“8012441555101” , GILLETTE FUSION PROGLIDE , 100 , P&G , False , NULL , THÙNG NƯ?C1 ,8000, 17,DVTINH | It miss check DVTinh be more 10 characters |  | UT-MHC01
UT-DF-MHC05 | KiemTraTruocKhiLuu(DataTable dtbMatHang, String cellString) | Thanh Tran, Tram Tran | Close | 1 | 1 | GIABAN is a negative number | Phuong Le | 2011-04-08 | Execute KiemTraTruocKhiLuu(DataTable dtbMatHang, String cellString) with parameters are: 2,“8012441555101”, GILLETTE FUSION PROGLIDE , 100 , P&G , False , NULL , CÁI ,-8000, 17,GIABAN | GIABAN must be position number, but when GIABAN < 0 this test case pass |  | UT-MHC01
MatHangData.cs
UT-DF-MHD01 | SaveToDB(string MaMH, string TenMH, string MaVach,string DonGiaMua, string DonGiaBan, string DonViTinh,string SoLuongTon, string NhaSanXuat,string MaNH) | Thanh Tran, Tram Tran | Close | 1 | 1 | It is inserted to database | Phuong Le | 2011-04-08 | Execute SaveToDB(string MaMH, string TenMH, string MaVach,string DonGiaMua, string DonGiaBan, string DonViTinh,string SoLuongTon, string NhaSanXuat,string MaNH) with parameters are: 2,“8012441555101”, GILLETTE FUSION PROGLIDE , 100 , P&G , False , NULL , CÁI ,-8000,0, 17,0 | GIABAN must be position number, but it be inserted to database |  | UT-MHD01
UT-DF-MHD02 | SaveToDB(string MaMH, string TenMH, string MaVach,string DonGiaMua, string DonGiaBan, string DonViTinh,string SoLuongTon, string NhaSanXuat,string MaNH) | Thanh Tran, Tram Tran | Close | 1 | 1 | It is inserted to database | Phuong Le | 2011-04-08 | Execute SaveToDB(string MaMH, string TenMH, string MaVach,string DonGiaMua, string DonGiaBan, string DonViTinh,string SoLuongTon, string NhaSanXuat,string MaNH) with parameters are: 2,“8012441555101”, D?u g?i đ?u ADVANCE TECHNIQUES Body Building Shampoo , 100 , P&G , False , NULL , CÁI ,8000,0, 17 | It miss check TenMH be more 50 characters |  | UT-MHD01